## Overview
Forecast
| Budget FY25 11.03.2024 (shared with P&O ECO DIG) |  | Budget FY25 (confirmed) |  | FC Q1 FY25 15.01.2025 |  | FC Q2 FY25 11.03.2025 |  | FC Q3 FY25 (current) |  | FC Q4 FY25 |  | Profit (in %)
| Costs | Price | Costs | Price | Costs | Price | Costs | Price | Costs | Price | Costs | Price
TMS Operations | 4200000 | 4330000 |  | 1650000 | 1279500 | 1650000 | 1325636 | 1650000
TMS Project: Eightfold Value Crew | 1288000 | 1385995 | 872500 | 908000 | 669035.05 | 703000 | 273489 | 287163
TMS Project: Ext. Careers Portal | 0 | 0 | 0 | 0 | 0 | 0 | 632250 | 663863
TMS Project: Avature Value Crew | 1107000 | 1188884 | 1408000 | 1453000 | 1399500 | 1473500 | 1314565 | 1380293
TMS Project: Avature Preboarding | 0 | 0 | 0 | 0 | 0 | 0 | 93359 | 98027
TMS Change Requests (CR)
TMS Sonderbudget SHS | 0 | 0 | 0 | 0 | 0 | 17269 | 18609 | 18609
Premisses for Budget FY25
Operations
SHS keeps using TMS in FY25; US/CA not using Avature effective 01.01.2025
Ramp down Eightfold until 30.09.2025; keep major vendors Avature, Tupu [acquired by eRoad])
additional topics compared to FY24: 1.) new integrations to monitor (HR D2GO, DirX, Workday, PDC); 2.) topics from CF A audit: EF Matching Model Monitoring; 3.) AV Self Config. --> tbd. T€
Productivity Target: 306 T€
Project
2 tester (250 T€); 2/3 TL (144 T€), Integration expert (70 T€), 2 IT SM (200 T€) to be covered by project budget --> 670 T€

## Resource Planning
Resource Planning
Names | GID | Role | Rate level | Intern/extern | Department | Country/ Location | Operations | Project Crew 1 (Eightfold) | Project Crew 2 (Avature) | Project Crew 3 (Avature ext. Careers) | Project Crew 4 (Preboarding) | Productive Hours/year | Prod Hours/week | Cost Rate | Sell Rate (Internal Customer) | Annual Costs | Comment
Helbing, Björn | Z000RN2U | Team Lead Talent Solutions | R9 | intern | GBS H2R DPS TMS | DE - MCH P | 30% | 5% | 30% | 30% | 5% | 1656 | 40 | 130 | 148
Fernandes Redondo, Amanda | Z003596V | IT Service Professional | R5 | intern | GBS H2R DPS TMS | ES - TRC E 5 | 100% | 0% | 0% | 0% | 0% | 1648 | 40 | 61.6 | 72.6
Zouine, Meryem | Z004UY1U | IT Service Professional | R5 | intern | GBS H2R DPS TMS | ES - TRC E 5 | 0% | 10% | 0% | 0% | 90% | 1648 | 40 | 61.6 | 72.6
Cerezo, Alberto | Z004X4HF | IT Service Professional | R5 | intern | GBS H2R DPS TMS | ES - TRC E 5 | 0% | 0% | 0% | 100% | 0% | 1656 | 40 | 61.6 | 72.6
Swoboda, Claudia | Z0005PKI | IT Service Professional | R5 | intern | GBS H2R DPS TMS | DE - MCH P | 60% | 0% | 0% | 0% | 0% | 1656 | 24 | 100 | 114 |  | 32h in total: 24h for TMS, 8h for Reward CS
Bicho, Rita | Z003RA2A | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | ES - TRC E 5 | 25% | 0% | 25% | 25% | 25% | 1648 | 40 | 61.6 | 72.6
Heinen, Anna | Z004PDTZ | Bachelor Student - Technical | R1 | intern | GBS H2R DPS TMS | DE - MCH P | 100% | 0% | 0% | 0% | 0% | 200 | 35 | 40 | 46 |  | Ellen De Groeve: we now agreed on the following as of FY25: Year 1 - no PCT-booking needed Year 2 - 200 hours Year 3 - 600 hours
Magro, Daniel | Z003WUKN | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 50% | 0% | 0% | 0% | 0% | 1700 | 40 | 45 | 59
Pires Rosa, Claudia (ext) | Z004NZ9C | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 0% | 10% | 0% | 90% | 0% | 1700 | 40 | 45 | 59
Matos Oliveira, Rita | Z004EJMV | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 0% | 0% | 75% | 0% | 0% | 1700 | 40 | 45 | 59
Pires, Filipe | Z004F2PT | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 0% | 0% | 100% | 0% | 0% | 1700 | 40 | 45 | 59
Plácido, Andreia | Z004FNPR | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 0% | 0% | 0% | 100% | 0% | 1700 | 40 | 45 | 59
Antunes, Ricardo | Z004JYNY | Tester | R5 | Nearshore | GBS DS BTA BPM TC BT | PT - ARA I | 100% | 0% | 0% | 0% | 0% | 1700 | 40 | 45 | 59
Minarcik, Jiri | Z004NEXK | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 43 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
Nová, Miroslava | Z004C3AF | IT Solution Expert | R7 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 45.6 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
Augusto da Silva, Amanda | Z004XNWB | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 43 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
Timkova, Jarmila | Z004RNSU | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 43 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
Strojny, Tomasz Lech | Z0050SBN | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 43 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
n.n. |  | IT Solution Expert | R5 | intern | GBS H2R DPS TMS | CZ - PRG S | 100% | 0% | 0% | 0% | 0% | 1680 | 40 |  | 43 |  | cost rate incl. 7,5% margin + 7,9% CPI increase (info Amir)
Matos, Paula | Z003CRJM | Support (XFS) |  | Nearshore | GBS DS TO IMS | PT - ARA I | 100% | 0% | 0% | 0% | 0% | 1700 | 40 | 46.25 | 125
Costa, Bruno | Z00475SU | Support (XFS) |  | Nearshore | GBS DS TO IMS | PT - ARA I | 100% | 0% | 0% | 0% | 0% | 1700 | 40 | 40 | 125
Conceicao, Ana (ext) | Z004RTZS | Support (XFS) |  | Nearshore | GBS DS TO IMS | PT - ARA I | 100% | 0% | 0% | 0% | 0% | 1700 | 40 | 40 | 125
Lomidze, Elizaveta |  | PowerBI Expert |  | extern | IT DA | DE - MCH P | [7 empty] | 150
Guerra Nobre, Mario Hugo
Kühlwetter, Esther |  | Scrum Master |  |  |  |  | 0% | 0% | 60% | 0% | 0% | 1656 | 24 | 130 | 148

## Operations
Fin. Transf. Cat. | Fin. DPS Plann. | PowerBI | P&O Cat. | FY25 - TMS Operation | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | Actual FC FY25 | confirmed costs 07/2024 | Difference | Comment
|  |  |  | Minarcik, Jiri | 6800 | 6720 | 2454 | 6544 | 6544 | 4254 | 5562 | 6217 | [5 empty] | 72833
|  |  |  | Nová, Miroslava | 3840 | 6400 | 6423 | 6944 | 6597 | 6597 | 7638 | 6597 | [5 empty] | 72833
|  |  |  | Augusto da Silva, Amanda | 6720 | 4880 | 3844.6 | 5848.7 | 6462 | 4376 | 3313 | 4499 | [5 empty] | 72833
|  |  |  | Timkova, Jarmila | 5760 | 6720 | 4908 | 6544 | 5849 | 6871 | 7199 | 3272 | [5 empty] | 68732
|  |  |  | Strojny, Tomasz Lech | 7198.4 | 6871.2 | 5235.2 | 4867.1 | 4867 | 6012 | 5153 | 3722 | [5 empty] | 68732
|  |  |  | Fernandes Redondo, Amanda | 2025-04-01: 182; 2025-05-01: 183
|  |  |  | n.n. | 0 | 0 | 0 | 0 | 0 | 0 | 694 | 0 | 0 | 0 | 0 | 0 |  | 68732
B |  | 5975 |  | Support/TMS Experts CZ - total - s.r.o. ARE 5975 | [15 empty] | 30.09.: In ISA-light between 5975 and 7092 total contract value of 356.100,- € (5 FTE) confirmed
|  |  |  | Support/TMS Experts CZ - charging to GBS CN H2R (China) | [13 empty] | -15938 |  | FY24: 24.710€ (already includes 7,5% CZ profit margin) for SIPCA, WD, TMS; FY25: 60% TMS only; +7,5% CZ PCI increase
|  |  |  | Support/TMS Experts CZ - charging to GBS H2R US (USA/Canada) | [13 empty] | -118450 |  | FY24: 103.000 €; FY25: +7,5% CZ profit margin +7,5% CZ PCI increase; when SHS will step out 20% reduction effictive next month (credit note)
| 4 |  | ExpCZ | Support/TMS Experts CZ - charging to P&O ECO DIG | [13 empty] | 289195 |  | 346.000 in FY24
|  |  |  | Matos, Paula | 8027 | 6568 | 6924 | 6998 | 7377 | 6232 | 7539 | 7354 | [5 empty] | 88400
|  |  |  | Costa, Bruno | 6720 | 6392 | 5440 | 7040 | 6400 | 6020 | 4600 | 5580 | [5 empty] | 88400
|  |  |  | Conceicao, Ana (ext) | 6800 | 5700 | 4160 | 6800 | 5920 | 6360 | 4320 | 6600 | [5 empty] | 88400
|  |  |  | Support SNOW | 2025-01-01: 1126; 2025-02-01: 1976; 2025-03-01: 1778; 2025-04-01: 615; 2025-05-01: 1799
|  |  |  | Others | 785 | 465 | 206 | 149 | 324 | 429 | 79 | 882 | [5 empty] | 0
C | 4 | 5240 | ExpPT | Support/TMS Experts PT - total - ARE 5240
|  |  |  | Magro, Daniel | 3960 | 3600 | 2880 | 3735 | 3420 | 1800 | 3600 | 3600 | [5 empty] | 44200
|  |  |  | Rosa, Claudia (ext) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0 |  | 0
|  |  |  | Matos Oliveira, Rita | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0 |  | 0
|  |  |  | Pires, Filipe | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0 |  | 0
|  |  |  | Plácido, Andreia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0 |  | 0
|  |  |  | Antunes, Ricardo | 8280 | 7200 | 5400 | 7920 | 7200 | 3600 | 0 | 0 | [5 empty] | 88400
C | 4 | 5240 | Test | Testing PT - ARE 5240
A | 5 |  |  | Helbing, Björn | 7289 | 5207 | 4859 | 6595 | 5206 | 6072 | 3120 | 2808 | [5 empty] | 71760 |  | ab April pro Monat Support CN 20 Std und US 72 Std
B | 4 | 5290 |  | Fernandes Redondo, Amanda | 9196 | 9683 | 7247 | 10231 | 9683 | 9013 | 8100 | 6638 | [5 empty] | 100363
B | 4 | 5290 |  | Zouine, Meryem | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 0 |  | compared to external ressource (125T€) -20%
B | 4 | 5290 |  | Cerezo, Alberto | 2024-10-01: 0; 2024-11-01: 122; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0
A | 5 |  |  | Swoboda, Claudia | 9100 | 8000 | 6300 | 7800 | 7200 | 8600 | 9800 | -10000 | [5 empty] | 91080 |  | ab April pro Monat 80 Std für Support US
B | 4 | 5290 |  | Bicho, Rita | 2606 | 1629 | 2932 | 2769 | 3257 | 3257 | 1950 | 3096 | [5 empty] | 33454
A | 5 |  |  | Heinen, Anna | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 1400
|  |  |  | IT Lease costs | 2024-11-01: 16.25; 2024-12-01: 3.75; 2025-01-01: 5; 2025-02-01: 7.5; 2025-03-01: 2.5; 2025-04-01: 12
E |  |  | Av | Avature Certification (PO 9708929580) | 2025-09-01: 15000 |  | 15000 |  |  |  | should be moved to Operations
F | 3 |  |  | DPS Internal Umlage (global) | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 | 9288 |  | 212375
|  |  | GBS | Service Management - ES- 5290 + int.
A |  |  |  | DirX
A |  |  |  | CHCM
A |  |  |  | JCC | 2024-10-01: 112; 2024-12-01: 53; 2025-03-01: 112; 2025-05-01: 493
A |  |  |  | Others | 2025-03-01: 590 |  | 0
| 3 |  | GBS | Change Management
E |  |  | TuP | Tupu (TRE) Renewal PO | [13 empty] | 53612
|  |  |  | SAG Subscription fee 5th year | 2024-12-01: 9759
|  |  |  | SAG/SHS Licenses 55 | 2024-12-01: 33749
E |  |  | eQ | eQuest - 109.000 € / PO 9708727251 | 9084 | 9084 | 9084 | 9084 | 9084 | 9084 | 9084 | 9084 | 9084 | 9084 | 9080 | 9080 |  | 109000
E |  |  |  | Premium Data Report for SAG
D |  |  | Adob | Adobe Sign |  |  | 25628 | 8543 | 8543 | 8543 |  | 8543 | 8543 | 8543 | 8543 |  |  | 50600 |  | Olgierd Dudko, 18.12.2024: 82.761,12 € / 27.02.2025: 75.900 € / credit note €6.900
| 2 |  | ext. Prov | Integrations external Provider
A |  |  |  | Siemens SMTP (Mailgateway Tupu) - MSGSMTP33691410220734 | 2024-10-01: 0; 2024-11-01: 1250 |  | 7500
A |  |  |  | Siemens SMTP (Mailgateway EF) - MSGSMTP33182209220509 |  | 4400 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 |  | 24000
A |  |  |  | Siemens SMTP (Mailgateway Avature) - MSGSMTP35971412220447 | [13 empty] | 24000 |  | charged together w/ Eightfold TIP
A |  |  |  | Wiki (TA Wiki; ALM Archive) | 2024-10-01: 0; 2024-12-01: 100; 2025-01-01: 300; 2025-02-01: 100; 2025-03-01: 100 |  | 2220
A |  |  |  | Siemens IT - GBS H2R DPS others (SCD Zusatzdienste for AV 1.100,- €) | 0 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 |  | 44796
|  |  |  | Siemens IT - GBS H2R DPS others (Certificates) | 2024-12-01: 140; 2025-03-01: 70
A |  |  |  | DirX (Avature: 1.601) | 0 | 3202 | 1601 | 1601 | 1601 | 1601 | 1601 | 1601 | 1601 | 1601 | 1601 | 1601 |  | 19212
A |  |  |  | Jira | 0 | 2000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 12000
A |  |  |  | JCC (Proxy for ICSR) | 0 | 945 | 472.5 | 472.5 | 472.5 | 472.5 | 472 | 472 | 472 | 472 | 472 | 472 |  | 5670
D |  |  |  | MyLearningWorld | [13 empty] | 0
D |  |  |  | SOC
| 3 |  | Int | Integrations SAG (internal booking)
|  |  | x | Integrations total
A | 5 |  |  | Audit (Moers, Holland) | [13 empty] | 0
D | 2 |  |  | Accessibility Testing | 2025-09-01: 10000 |  | 10000
D | 2 |  |  | CERT Check | 2025-09-01: 10000 |  | 10000 |  | Pentest for JCC Proxy after AWS Migration
C | x |  |  | Translations
D | x |  |  | Travel & Hospitality
|  |  | GBS | Additional costs
|  |  | GBS | GBS total
|  |  |  | Operations - total costs for P&O ECO DIG | [16 empty] | Revenue P&O | 1650000
Profit Margin
|  |  |  | Operations - total costs for PowerBI reporting | [16 empty] | Revenue total
|  |  |  | (incl. P&O / US / CN) | [16 empty] | Profit Margin
[5 empty] | P01 | P02 | P03 | P04 | P05 | P06 | P07 | P08 | P09 | P10 | P11 | P12
Legend |  |  |  | DPS Reporting - ACT Cost | P02: 104271.93; P03: 216618.98; P04: 100246.07; P05: 98668.13; P06: 224783.83; P07: 104223.11; P08: 93644.22
Forecast |  |  |  | DPS Reporting - ACT Cost YTD | P08: 942456.27
Actuals
|  |  |  | Revenue Charging |  |  | 412500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500
2326
A |  |  |  | DPS internal costs (including DPS internal services) '- Germany
B |  |  |  | DPS cost from another country (internal + external) '- ES and CZ
C |  |  |  | External cost time and material (external to DPS) '- PT
D |  |  |  | External cost fix (external to DPS) '- non DPS
E |  |  |  | External provider
F |  |  |  | Licenses and subscription fees
| 1 |  |  | 01_Revenue
| 2 |  |  | 02_External (3rd party supplier/provider, Adobe)
| 3 |  |  | 03_Internal Booking (Umlage, costs allocation from other DE DPS chapters eg. JCC, DirX etc.)
| 5 |  |  | 05_DPS Pers (hours reported by DE DPS colleagues )
| 4 |  |  | 04_Provision Hours (non-DE DPS colleagues eg. ES/CZ and non-DPS- non-DE PT etc. )
|  |  | Adob | Addons - Adobe Sign
|  |  | eQue | Addons - eQuest
|  |  | Tup | Addons - Tupu
|  |  | Int | Addons - Siemens Integrations
|  |  | GBS | GBS H2R DPS SM
|  |  | Test | Test
|  |  | ExpCZ | Support/TMS Experts CZ
|  |  | ExpPT | Support/TMS Experts PT
P&O direct ordering
|  |  |  | Avature Total - | P01: 1790271
|  |  |  | Eightfold - | P01: 810000
|  |  |  | Eightfold - 30.000 for 3rd instance | P01: 30000
Note on M16: Swoboda, Claudia (GBS H2R DPS 2 1): Manual ticket transfer to SNOW from FNOW ticket
Note on F17: Swoboda, Claudia (GBS H2R DPS 2 1): Internal 260,00
Note on G17: Swoboda, Claudia (GBS H2R DPS 2 1): Internal 310,00
Note on H17: Swoboda, Claudia (GBS H2R DPS 2 1): Internal 130,00
Note on K17: Swoboda, Claudia (GBS H2R DPS 2 1): Internal 570,00
Note on M30: Swoboda, Claudia (GBS H2R DPS 2 1): Korrektur für April: 100 Std auf SB US deshalb keine Std.buchung für Mai auf OP
Note on L47: Swoboda, Claudia (GBS H2R DPS 2 1): Adobe 8.543 - 18.809,35 (Gutschrift PEP Projekt, Okt - Mrz)
Note on E49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://wiki.siemens.com/display/en/H2R+DPS+Mail+Services
Note on K52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cancellation effective March 31st
Note on E55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Charging only for integrations target systems; no payment for Ef and Tupu

## Fin. DPS Plann.
Stand 18.03.2025 |  | Category
Topic | Type | 00_Actuals P04 | 01_FC Q1 | 02_FC Q2 | 03_BDG 26
TMS Project, Projekt | 01_Revenue | 232414.17 | 2395000 | 2429500 | 2128500
| 02_External | -233635.75 |  | 0 | 0
| 03_Internal Booking | -59982.89 |  | 0 | 0
| 05_DPS Pers | -47810.1 | -2280000 | -2313662 | -2027000
| 04_Provision Hours | -160342.85 |  | 0 | 0
TMS Project, Projekt Ergebnis |  | -269357.42 | 115000 | 115838 | 101500
TMS, OP | 01_Revenue | 550000 | 1650000 | 1650000 | 1550000
| 02_External | -80397.89 |  | 0 | 0
| 03_Internal Booking | -98892.28 |  | 0 | 0
| 05_DPS Pers | -56569.9 | -1570000 | -1325635 | -1475000
| 04_Provision Hours | -185276.91 |  | 0 | 0
TMS, OP Ergebnis |  | 128863.02 | 80000 | 324365 | 75000
TMS, SB | 01_Revenue |  | 5000 | 18609 | 15000
| 02_External |  |  | 0 | 0
| 03_Internal Booking |  |  | 0 | 0
| 05_DPS Pers |  | -5000 | -18609 | -14200
| 04_Provision Hours | -8538.2 |  | 0 | 0
TMS, SB Ergebnis |  | -8538.2 | 0 | 0 | 800
|  | -148513.1 | 194000 | 440203 | 177300
Aligned with Iva: 18.03.2025 |  | Category
Topic | Type | 00_Actuals P04 | 01_FC Q1 | 02_FC Q2 | 03_BDG 26
TMS Project, Projekt | 01_Revenue | 232414.17 | 2395000 | 2429500 | 2113250
| 02_External | -233635.75 |  | -1376158 | -1175000
| 03_Internal Booking | -59982.89 |  | -225259 | -231566
| 05_DPS Pers | -47810.1 | -2280000 | -167764 | -133142
| 04_Provision Hours | -160342.85 |  | -544481 | -442062
TMS Project, Projekt Ergebnis |  | -269357.42 | 115000 | 115838 | 101500
TMS, OP | 01_Revenue | 550000 | 1650000 | 1650000 | 1571700
| 02_External | -80397.89 |  | -248429 | -224000 | TuP, eQ, Adob, Cys, Av Trv
| 03_Internal Booking | -98892.28 |  | -214199 | -337000 | Umlage, Integr.,
| 05_DPS Pers | -56569.9 | -1570000 | -168105 | -193500 | Trv
| 04_Provision Hours | -185276.91 |  | -694902 | -742500 | DPS CZ, ES, Trv
TMS, OP Ergebnis |  | 128863.02 | 80000 | 324365 | 75000
Preboarding Project, Projekt | 01_Revenue |  |  |  | tbd
02_External
03_Internal Booking
05_DPS Pers
04_Provision Hours

## Project
Fin. Transf. Cat. | Fin. DPS Plann. | PowerBI | P&O Cat. | FY25 TMS Project | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | Actual FC FY25 | FC FY25 (01/2025) | FC FY25 (11/2024) | Budget FY25 (May 2024) | Differenz | Comment
|  |  | x | Eightfold Crew
C |  |  |  | Magro, Daniel | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
C |  |  |  | Pires Rosa, Claudia | 8280 | 5400 | 3600 | 7920 | 7200 | 7560 | 720 | 360 | [5 empty] | 76200 | 76500
C |  |  |  | Matos dos Santos Oliveira, Ana Rita | 2024-10-01: 5400; 2024-11-01: 5400; 2024-12-01: 3510; 2025-01-01: 5400; 2025-02-01: 4860; 2025-03-01: 4050; 2025-04-01: 0 |  | 57960 | 57375
C |  |  |  | Pires, Filipe | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Plácido, Andreia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
C |  |  |  | Antunes, Ricardo | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
| 4 | 5240 |  | Test - ARE 5240
A | 5 | int |  | Helbing, Bjoern | 7262 | 5187 | 4841 | 6310 | 5187 | 4755 | 520 | 468 | [5 empty] | 71440 | 71760
B | 4 | 5290 |  | Fernandes Redondo, Amanda | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
B | 4 | 5290 |  | Zouine, Meryem | 9520 | 8400 | 10080 | 9331 | 6895 | 0 | 1435 | 0 | [5 empty] | 104448.8667 | 101517
B | 4 | 5290 |  | Cerezo, Alberto | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
A | 5 | int |  | Swoboda, Claudia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
B | 4 | 5290 |  | Lazaro Bicho, Rita Sofia | 2596 | 1623 | 2921 | 1835 | 1997 | 1400 | 527 | 403 | [5 empty] | 31534.2889 | 33839
F | 3 |  |  | DPS Internal Umlage (global) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134832 |  |  |  | Erhöhung Umlage im Projekt
Service Management - ARE 5290 + int.
A |  |  |  | JCC | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 5000 | 5000 | 5000
A |  |  |  | CHCM (Eviden) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 10000 | 10000 | 10000
A |  |  |  | AWS Encryption Key (KMS for Eightfold; GBS) | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  | 600
A |  |  |  | DirX (Ext)/(SAG Global) | 2024-10-01: 1634; 2024-11-01: 23; 2024-12-01: -35; 2025-01-01: 805; 2025-02-01: 0 |  | 20000 | 20000 | 20000
| 3 |  |  | Integrations DPS
|  |  | GBS | GBS total
E |  |  | TuP | TRE (Tupu) PO | [13 empty] | 0 | 0
E |  |  | 8F | Eightfold (PO Q1/2025: 9708791569; Q2-Q4: tbd.) | 30495 | 24259 | 20419.5 | 20732.75 | 7706.5 | 2392.25 | 316.75 | 90.5 | [5 empty] | 114994.25 | 300000 | 300000 |  | 1st Quarter (140.442 €)
| 2 |  | x | Provider | [13 empty] | 114994.25
D | 2 |  | TCYS | CERT check (pen GBS) | 2025-09-01: 0 |  | 0 | 0 | 0
D | 2 |  | TCYS | Accessibility Test | 2025-09-01: 0 |  | 10000 | 10000 | 10000
D |  |  | Trv | Travel & Hospitality | 2025-09-01: 0 |  | 50000 | 50000 | 50000
|  |  | x | Additional costs | [13 empty] | 60000
|  |  | x | Total Costs | [18 empty] | Revenue
|  |  | x | Accumulated costs Eightfold Crew | [18 empty] | Profit Margin | 5%
x
|  |  | x | Avature Crew
C |  |  |  | Magro, Daniel | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
C |  |  |  | Rosa, Claudia (ext) | 2024-10-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
C |  |  |  | Matos Oliveira, Rita | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-04-01: 4320; 2025-05-01: 5400 |  | 0 | 0
C |  |  |  | Pires, Filipe | 7920 | 6840 | 5760 | 6120 | 6840 | 3240 | 5400 | 5400 | [5 empty] | 77640 | 76500
C |  |  |  | Plácido, Andreia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Antunes, Ricardo | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
| 4 | 5240 |  | Test - ARE 5240
A | 5 | int |  | Helbing, Björn | 7289 | 5207 | 4859 | 6595 | 5207 | 6072 | 3380 | 2808 | [5 empty] | 71790 | 71760
B | 4 | 5290 |  | Fernandes Redondo, Amanda | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
B | 4 | 5290 |  | Zouine, Meryem | 0 | 0 | 0 | 0 | 2135 | 0 | 7648 | 1050 | [5 empty] | 0 | 0
B | 4 | 5290 |  | Cerezo, Alberto | 2024-10-01: 9988; 2024-11-01: 7186; 2024-12-01: 3898; 2025-01-01: 7308; 2025-02-01: 2436; 2025-03-01: 305; 2025-04-01: 0 |  | 96385.4 | 102009.6
A | 5 | int |  | Swoboda, Claudia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0 | 0
B | 4 | 5290 |  | Bicho, Rita | 2606 | 1629 | 2932 | 2605 | 3124 | 3123 | 1954 | 3074 | [5 empty] | 31842.2889 | 33838.9333
F | 3 |  |  | DPS Internal Umlage (global) | [13 empty] | 44940 |  |  |  | Erhöhung Umlage im Projekt
Service Management - ARE 5290 + int.
A |  |  |  | JCC | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-09-01: 5000 |  | 5000 | 5000 | 5000
A |  |  |  | CHCM (Eviden) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-06-01: 5000; 2025-09-01: 5000 |  | 10000 | 10000 | 10000 |  | Anpassung im Rahmen Migr zu AWS
|  |  |  | DirX PT - 5240 | 2025-04-01: 1211; 2025-05-01: 115
A |  |  |  | DirX (Eviden) | 2024-10-01: 57.5; 2024-12-01: 289; 2025-01-01: 1074; 2025-02-01: 657; 2025-03-01: 1793 |  | 5000 | 10000 | 10000
| 3 |  |  | Integrations DPS
|  |  | GBS | GBS total
E |  |  | TuP | TRE (Tupu) (PO tbd) | 2025-09-01: 9500 |  | 30000 | 30000 | 30000
E |  |  | 8F | Eightfold | 2025-09-01: 0 |  | 0 | 0 | 150000
E |  |  | Av | Avature DT (PO 9708872111) | 93901.5 | 79227.75 | 102582.38 |  | 101200.05 |  | 57164.63 | 80805.9 | 79995.3 | 64881.86 | 62401.5 | 69195 |  | 965493.38 | 1002000 | 578500 |  | W2P effort: 313 hours
E |  |  | Av | Avature AM (PO 9708872111) | 2024-12-01: 375; 2025-02-01: 3052; 2025-03-01: 3534; 2025-04-01: 1116 |  | 20000 | 0
|  |  | Av | Avature Healthcheck (PO
| 2 |  | x | Provider
D | 2 |  | TCYS | CERT check (pen GBS) | [13 empty] | 0 | 0
D | 2 |  | TCYS | Accessibility Test | 2025-09-01: 10000 |  | 10000 | 10000 | 10000
D |  |  | Trv | Travel & Hospitality | [13 empty] | 0 | 0
|  |  | x | Additional costs
|  |  | x | Total costs | [18 empty] | Revenue
|  |  | x | Accumulated costs Avature Crew | [18 empty] | Profit Margin | 5%
|  | x | x
|  |  | x | Avature ext. Careers Portal Crew
C |  |  |  | Magro, Daniel | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Pires Rosa, Claudia (ext) | 0 | 0 | 0 | 0 | 0 | 0 | 6480 | 3240 | [5 empty] | 0
C |  |  |  | Matos Oliveira, Rita | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Pires, Filipe | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Moreira Cristo Placido, Andreia Sofia | 0 | 0 | 0 | 0 | 0 | 3744 | 7200 | 7200 | [5 empty] | 0
C |  |  |  | Antunes, Ricardo | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
| 4 | 5240 |  | Test - ARE 5240 | [13 empty] | 0
A | 5 | int |  | Helbing, Björn | 0 | 0 | 0 | 0 | 0 | 1560 | 3380 | 2808 | [5 empty] | 0
B | 4 | 5290 |  | Fernandes Redondo, Amanda | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 183; 2025-04-01: 0 |  | 0
B | 4 | 5290 |  | Zouine, Meryem | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
B | 4 | 5290 |  | Cerezo, Alberto | 0 | 0 | 0 | 0 | 7308 | 7004 | 7308 | 7308 | [5 empty] | 0
A | 5 | int |  | Swoboda, Claudia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
B | 4 | 5290 |  | Bicho, Rita | 0 | 0 | 0 | 325 | 519 | 1586 | 3743 | 2699 | [5 empty] | 0
F | 3 |  |  | DPS Internal Umlage (global) | [13 empty] | 44940 |  |  |  | Erhöhung Umlage im Projekt
|  |  |  | Service Management - ARE 5290 + int. | [13 empty] | 0
A |  |  |  | JCC | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 0
A |  |  |  | CHCM (Evdien) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-04-01: 112 |  | 0
A |  |  |  | DirX (Eviden) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 0
| 3 |  |  | Integrations DPS | [13 empty] | 0
|  |  | GBS | GBS total
|  |  |  | Avature ext. Careers Portal (PO 9709043748) - PDP | 2025-05-01: 74655
E |  |  | Av | Avature ext. Careers Portal (PO 9709132497) | 2025-05-01: 57196; 2025-06-01: 57196; 2025-07-01: 57196; 2025-08-01: 57196 |  | 0
| 2 |  | x | Provider | [13 empty] | 0
D | 2 |  | TCYS | CERT check (pen GBS) | 2025-09-01: 10000 |  | 0
D | 2 |  | TCYS | Accessibility Test | [13 empty] | 0
D | 2 |  | Trv | Travel & Hospitality ext. Provider | 2025-06-01: 1800; 2025-09-01: 7000 |  | 0
| 6 |  | Trv | Travel & Hospitality DE | 2025-09-01: 5000
| 4 |  | Trv | Travel & Hospitality ES / CZ / PT | 2025-09-01: 13000
|  |  | x | Additional costs | [13 empty] | 0
|  |  | x | Total costs | [13 empty] | 0 |  |  |  |  | Revenue
|  |  | x | Accumulated costs Ext. Careers Port Crew | [13 empty] | 0 |  |  |  |  | Profit Margin | 5%
|  | x | x
|  |  | x | Avature Preboarding
C |  |  |  | Magro, Daniel | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Rosa, Claudia (ext) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Matos Oliveira, Rita | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Guerreiro Luis Pires, Filipe Viegas | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | [5 empty] | 0
C |  |  |  | Plácido, Andreia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
C |  |  |  | Antunes, Ricardo | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
| 4 | 5240 |  | Test - ARE 5240 | [13 empty] | 0
A | 5 | int |  | Helbing, Björn | 0 | 0 | 0 | 260 | 0 | 260 | 520 | 468 | [5 empty] | 0
B | 4 | 5290 |  | Fernandes Redondo, Amanda | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
B | 4 | 5290 |  | Zouine, Meryem | 0 | 0 | 0 | 1001 | 1470 | 0 | 2678 | 6370 | [5 empty] | 0
B | 4 | 5290 |  | Cerezo, Alberto | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
A | 5 | int |  | Swoboda, Claudia | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
B | 4 | 5290 |  | Bicho, Rita | 0 | 0 | 0 | 1739 | 863 | 393 | 122 | 0 | [5 empty] | 0
|  |  |  | Service Management | [13 empty] | 0
A |  |  |  | JCC | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
A |  |  |  | CHCM (Eviden) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
A |  |  |  | DirX (Eviden) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
| 3 |  |  | Integrations DPS | [13 empty] | 0
|  |  | GBS | GBS total
E |  |  | Av | Avature | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0 |  | 0 |  |  |  | costs for Avature tbd.
| 2 |  | x | Provider | [13 empty] | 0
D | 2 |  | TCYS | CERT check (pen GBS) | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
D | 2 |  | TCYS | Accessibility Test | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
D |  |  | Trv | Travel & Hospitality | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0 |  | 0
|  |  | x | Additional costs | [13 empty] | 0
|  |  | x | Total costs | [13 empty] | 0 |  |  |  |  | Revenue
|  |  | x | Accumulated costs Preboarding | [13 empty] | 0 |  |  |  |  | Profit Margin | 5%
|  |  |  | Total | [18 empty] | Revenue |  | 2100000 | P&O ECO DIG target
|  |  |  | Accumulated Total | [18 empty] | Profit Margin | 5% |  | Delta
Legend |  |  |  |  | 2025-03-01: P06
Actuals |  |  |  | ACT Cost YTD | 2025-03-01: 940328.64; 2025-04-01: 1105959
Approved
Forecast
|  |  |  | Avature | 2025-04-01: 132808
Eightfold
TuPu
Note on K20: Swoboda, Claudia (GBS H2R DPS 2 1): BSD-97 Bestellung Master Key: Verrechnung bei Frau Blei, Monika angefragt
Note on H21: Swoboda, Claudia (GBS H2R DPS 2 1): Removing hours from the incorrect PCT element for the 1Q 2025
Note on G25: Swoboda, Claudia (GBS H2R DPS 2 1): #INV2134 (korrigierte Rechnung am 17.12.2024 freigegeben)
Note on I25: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 01/25 gemeldet INV2336 reklamiert Neue Rechnung INV2336A am 05.05.2025 freigegeben
Note on J25: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 02/25 gemeldet INV2336 reklamiert Neue Rechnung INV2336A am 05.05.2025 freigegeben
Note on K25: Swoboda, Claudia (GBS H2R DPS 2 1): INV2337 vom 11.04.2025
Note on L25: Swoboda, Claudia (GBS H2R DPS 2 1): VLL für 04/25
Note on L44: Swoboda, Claudia (GBS H2R DPS 2 1): inkl. Nachbuchung für Mrz
Note on F58: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02246 20.12.2024
Note on G58: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02246 20.12.2024
Note on H58: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02268 vom 23.01.2025
Note on I58: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE002300 vom 26.02.2025
Note on J58: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 02/25 gemeldet Invoice DE02329 vom 27.03.2025
Note on K58: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 03/25 gemeldet Invoice DE02342 vom 09.04.2025 = €55781 Sonderbudget SHS €15.929 Avature Crew € 39.852
Note on L58: Swoboda, Claudia (GBS H2R DPS 2 1): VLL für 04/25 gemeldet Rg. DE02402 vom 06.06.2025
Note on G59: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02246 20.12.2024
Note on H59: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02268 vom 23.01.2025
Note on J59: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02329 vom 27.03.2025
Note on K59: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02343 vom 10.04.2025 reklamiert von Greg und Björn als ok bestätigt
Note on K90: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 03/25 €37.500 gemeldet
Note on L90: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 04/25 €37.500 gemeldet
Note on M91: Swoboda, Claudia (GBS H2R DPS 2 1): Rechnung DE02379 vom 13.05.2025
Note on N95: Swoboda, Claudia (GBS H2R DPS 2 1): Avature Reisekosten Workshop Lisbon (PO 9708872111 )
Note on L134: Swoboda, Claudia (GBS H2R DPS 2 1): + 57.000 Avature für April - 16.000 Avature aus Mrz (auf SHS)

## 8fold INV
FY25 TMS Project | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
Eightfold Brandreport
Rechnungen | 2024-10-01: 30324.75; 2024-11-01: 24259; 2024-12-01: 20419.5; 2025-01-01: 20732.75; 2025-02-01: 7706.5; 2025-03-01: 2392.25
|  |  |  | 21259.25 | 28439.25
28892.8
Gutschriften | 2025-02-01: 21259.25
Hallo Frau Prochazkova,
ich werde Rechnung(en) und Gutschrift mit Eightfold klären.
vielen Dank für Ihre Unterstützung.
Liebe Grüße
Claudia
Note on C3: Swoboda, Claudia (GBS H2R DPS 2 1): #INV2134 (korrigierte Rechnung am 17.12.2024 freigegeben)
Note on E3: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 01/25 gemeldet INV2336 reklamiert
Note on F3: Swoboda, Claudia (GBS H2R DPS 2 1): VLL 02/25 gemeldet INV2336 reklamiert
Note on G3: Swoboda, Claudia (GBS H2R DPS 2 1): INV2337 vom 11.04.2025
Note on E4: Swoboda, Claudia (GBS H2R DPS 2 1): INV2238
Note on F4: Swoboda, Claudia (GBS H2R DPS 2 1): INV2336A
Note on F5: Swoboda, Claudia (GBS H2R DPS 2 1): INV2336
Note on F6: Swoboda, Claudia (GBS H2R DPS 2 1): CM 212 für INV2238

## Travel Costs
Workshop Title | Time | Employee/ Type of Costs | Category | Planned Costs | Actual Costs
"One Careers" Workshop | 31.03. - 04.04.2025 | Test Team + Bruno | 4 | 3000
"One Careers" Workshop | 31.03. - 04.04.2025 | Facilities
"One Careers" Workshop | 31.03. - 04.04.2025 | Avature | 2 | 2000
15100
Total

## FC + Rev
nicht mit P&O teilen
TMS Landscape - Budget Project and Operation
Cat. |  | Budget FY25 03.2024 | an Steffi 03.2024 | Planned Costs FY25 07.2024 | Planned Costs FY25 - New 11.2024 | Marge |  | Revenue | an Steffi 11.2024 | Planned Costs FY25 - New 12.2024 | Marge |  | Revenue | an Steffi 12.2024 | Forecast Q1 | Marge |  | Revenue | an Steffi 01.2025 | Forecast Q2 (freeze 11.03.2025) | Marge |  | Revenue | an Steffi 11.03.2025 | Forecast Q3 (freeze) | Marge |  | Revenue | an Steffi 23.06.2025 | Forecast Q4 (running/ actuals) | Marge |  | Revenue | an Steffi dd.08.2025
| Project Ext. Careers Portal (form. Eightfold) Crew | SAG |  | SAG |  | % | EUR |  |  |  | % | EUR |  |  |  | % | EUR |  |  |  | % | EUR |  |  |  | % | EUR |  |  |  | % | EUR
AV | Avature | 578500 | 610000 | 578500 | 0 | 5% |  |  | 0 |  | 5% |  |  | 0 | 0 | 5% |  |  | 0 | 240000 | 5% |  |  | 252000 | 303439 | 5% |  |  | 319000 |  | 5% |  |  | 319000 | 303439
8F | Eightfold SoW + CRs | 150000 | 160000 | 150000 | 300000 | 5% |  |  | 315000 | 300000 | 5% |  |  | 315000 | 100000 | 5% |  |  | 105000 | 114003 | 5% |  |  | 119700 |  | 5% |  |  | 120000 |  | 5% |  |  | 120000 | 115085
GBS | GBS H2R DPS | 498500 | 525000 | 498500 | 503800 | 5% |  |  | 530000 | 512500 | 5% |  |  | 538125 | 509000 | 5% |  |  | 535000 | 516735 | 5% |  |  | 542500 |  | 5% |  |  | 521000 |  | 5% |  |  | 521000 | 496121
TCYS | T (CYS & Access.) | 10000 | 10500 | 10000 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 |  | 5% |  |  | 10500 |  | 5% |  |  | 10500 | 10000
Trv | Travel costs | 50000 | 52500 | 50000 | 50000 | 5% |  |  | 52500 | 50000 | 5% |  |  | 52500 | 50000 | 5% |  |  | 52500 | 25000 | 5% |  |  | 26000 |  | 5% |  |  | 26000 |  | 5% |  |  | 26000 | 25000
Total
Project Avature Crew
AV | Avature SOW + CRs | 578500 | 610000 | 578500 | 1001280 | 5% |  |  | 1052000 | 1013000 | 5% |  |  | 1071000 | 1016000 | 5% |  |  | 1071000 | 992655 | 5% |  |  | 1042300 |  | 5% |  |  | 1002000 |  | 5% |  |  | 1002000 | 953940
8F | Eightfold | 150000 | 160000 | 0 | 0 | 5% |  |  |  | 0 | 5% |  |  |  | 0 | 5% |  |  | 0 | 0 | 5% |  |  | 0 | 0 | 5% |  |  |  | 0 | 5% |  |  |  | 0
TuP | Tupu | 30000 | 31500 | 30000 | 30000 | 5% |  |  | 31500 | 30000 | 5% |  |  | 31500 | 30000 | 5% |  |  | 31500 | 9500 | 5% |  |  | 10000 |  | 5% |  |  | 10000 |  | 5% |  |  | 10000 | 9500
Oth | Other ext. providers | 0 | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0
GBS | GBS H2R DPS | 337000 | 355000 | 337000 | 342500 | 5% |  |  | 359000 | 355000 | 5% |  |  | 365000 | 343500 | 5% |  |  | 360500 | 395768 | 5% |  |  | 416000 |  | 5% |  |  | 383000 |  | 5% |  |  | 383000 | 364353
TCYS | T (CYS & Access.) | 10000 | 10500 | 10000 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 | 10000 | 5% |  |  | 10500 |  | 5% |  |  | 10500 |  | 5% |  |  | 10500 | 10000
Trv | Travel Costs | [8 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total
Total sum
[24 empty] | Target 2'1 |  |  |  |  | Target 2'1 |  |  |  |  | Target 2'1
TA/TM Product - Service Mgmt & Operations
Subscription Fee + Addons
AV | AVATURE | 1771000 | 1771000 | 0 | 0 | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  | 372000 |  | 0% |  |  | 372000 |  | 0% |  |  | 372000 |  | 0% |  |  | 372000
8F | Eightfold | 840000 | 840000 | 0 | 0 | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0%
Adob | Addons - Adobe Sign | 350400 | 53000 | 50600 | 50600 | 5% |  |  | 53130 | 50600 | 5% |  |  | 53130 | 50600 | 5% |  |  |  | 75921 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
eQ | Addons - eQuest |  | 115000 | 109000 | 109000 | 5% |  |  | 114450 | 109000 | 5% |  |  | 114450 | 109000 | 5% |  |  |  | 109000 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
TuP | Addons - Tupu |  | 56000 | 54000 | 54000 | 5% |  |  | 56700 | 43508 |  |  | 56700 | 56700 | 43508 | 5% |  |  |  | 43508 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
Integr | Addons - Siemens Integrations |  | 145000 | 140000 | 140000 | 5% |  |  | 147000 | 140000 | 5% |  |  | 147000 | 140000 | 5% |  |  |  | 102578 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
| JCC (SAG & SE) | 0 |  | 0 |  |  | included in Addons | included in Addons |  |  |  | included in Addons | included in Addons |  | 0 |  | included in Addons | included in Addons |  | 0 |  | included in Addons | included in Addons |  | 0 |  | included in Addons | included in Addons |  | 0 |  | included in Addons | included in Addons
Total
GBS H2R GBS
GBS | GBS H2R DPS SM | 1279600 | 600000 | 530000 | 541000 | 5% |  |  | 568050 | 541000 | 5% |  |  | 568050 | 541000 | 5% |  |  | 1279500 | 433104 | 5% |  |  | 1279500 |  | 5% |  |  | 1279500 |  | 5% |  |  | 1279500
Test | Test |  | 185000 | 132000 | 132000 | 5% |  |  | 138600 | 132000 | 5% |  |  | 138600 | 132000 | 5% |  |  |  | 120533 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
ExpCZ | Support/TMS Experts CZ |  | 280000 | 289195 | 289195 | 5% | 6580 |  | 295775 | 289195 | 5% | 6580 |  | 295775 | 289195 | 5% |  |  |  | 213821 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
ExpPT | Support/TMS Experts PT |  | 285000 | 265200 | 265000 | 5% |  |  | 278000 | 265000 | 5% |  |  | 278000 | 265000 | 5% |  |  |  | 227171 | 5% |  |  |  |  | 5% |  |  |  |  | 5%
Total
Service Mgmt. & Operations Total
| Abgestimmtes Budget | 4005000 | 4330000 |  |  |  |  | 1650000 | 1650000 |  |  |  | 1650000 | 1650000 |  |  |  | 1650000 | 1650000 |  |  |  | 1650000 | 1650000 |  |  |  | 1650000 | 1650000 |  |  |  | 1650000 | 1650000
Total

## Steffi
TMS
|  |  | Budget FY25 07.2024 | Budget FY25 07.11.2025 | FY25/Q1 FC 15.01.2025 | FY25/Q2 FC 11.03.2025 | FY25/Q3 FC 23.06.2025 | FY25/Q4 FC 12.08.2025 | FY26 Budget Stand 03/2025 | Comments
Ext. Careers Portal Crew | PCT-Elemente DPS | PSP Elements P&O ECO DIG | SAG (incl. SMO, SHS) | SAG (incl. SMO, SHS) |  | SAG (incl. SMO, SHS) | SAG (incl. SMO, SHS) | SAG (incl. SMO, SHS) | SAG (incl. SMO, SHS)
Avature |  | -- | 162000 | 0 | 0 | 252000 | 319000 |  | tbd. | FY26: Re-Launch Internal Careers Re-Launch Hiring Manager Portal Avature Copilot Functionalities Integration to Preboarding Sourcing integration (LinkedIn) MS Teams Connectivity Realising Health Check Measures Design one “AI-first”-segment (SPE Roll-Out, most probably not on ECOP DIG Budget) (Workday Fit-Gap Analysis - Next Steps)
Eightfold |  | -- | 315000 | 315000 | 105000 | 119700 | 120000 |  | tbd. | no EF rampdown costs considered
GBS H2R DPS |  | IP-HOTSG-TMS-DPS | 699000 | 530000 | 535000 | 542500 | 521000 |  | tbd.
T (CYS & Access.) |  | IP-HOTSG-TMS-TCY | 55000 | 10500 | 10500 | 10500 | 10500 |  | tbd.
Travel Costs |  | IP-HOTSG-TMS-TRV | 55000 | 52500 | 52500 | 26000 | 26000 |  | tbd.
Total
Avature Crew | PCT-Elemente DPS | PSP Elements P&O ECO DIG
Avature |  | IP-HOTSG-TMS-AVA |  | 1052000 | 1071000 | 1042300 | 1002000 |  | tbd. | FY25: incl. Avature Healthcheck FY26: additional recurring fees to consider: - ext. Careers portal (372 T€) - LinkedIn CRM (?) - XML feeds (10 T€) - Sherlock, Junction, Compound Objects, … (100 T€)
Tupu |  | IP-HOTSG-TMS-TUP | 33000 | 31500 | 31500 | 10000 | 10000 |  | tbd.
Other ext. providers |  | wird bei Bedarf angelegt | 0 | 0 | 0 |  |  |  | tbd.
GBS H2R DPS |  | IP-HOTSG-TMS-DPS | 196000 | 359000 | 360500 | 416000 | 383000 |  | tbd.
T (CYS & Access.) |  | IP-HOTSG-TMS-TCY | 10500 | 10500 | 10500 | 10500 | 10500 |  | tbd.
Travel Costs | [8 empty] | tbd.
Total
Project - total | [9 empty] | FY25 confirmed by P&O ECO DIG: 2'1 € FY26 confirmed by P&O ECO DIG: tbd.
Workday Recruiting / Gap analysis | [5 empty] | 165000 |  |  |  | handled by P&O ECO DIG
Scrum Master | [5 empty] | 55000 |  |  | 135000 | handled by P&O ECO DIG
Subscription Fees + Siemens Integrations | PCT-Elemente DPS | PSP Elements P&O ECO DIG
Avature | non GBS |  | 1771000 | 0 | 0 |  |  |  |  | handled by P&O ECO DIG
Eightfold | non GBS |  | 888000 | 0 | 0 |  |  |  |  | handled by P&O ECO DIG
Adobe Sign |  | IP-HOTSO-4SX-JIL | 378000 | 372000 | 372000 | 372000 | 372000 |  | tbd.
eQuest
Tupu
Siemens Integrations
Total
GBS H2R DPS
Service Management |  | IP-HOTSO-4CX-GSI | 1113000 | 1279500 | 1279500 | 1279500 | 1279500 |  | tbd.
Test
Support/TMS Experts CZ/PT
Total
Operations - total | [9 empty] | FY25 confirmed by P&O ECO DIG: 1'650 FY26 confirmed by P&O ECO DIG: tbd.
Project & Operations - total DPS |  |  |  | 1650000
IP-HOTSG-TMS-W2P

## Sonderbudget
Fin. Transform. Cat. | FY25 SHS Data extract |  | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | Actual FC FY25 | Planned costs (10.06.2024) | Differenz | Comment
| Helbing, Björn |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fernandes Redondo, Amanda |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Zouine, Meryem |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cerezo, Alberto |  | 1218 | 122 | 0 | 0 | 0 | 0 | 0 | 0
| Swoboda, Claudia |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Loerinc, Jan (ext) (Accenture) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bicho, Rita |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GBS | [23 empty] | FY24: 2.712,40 €
| Avature |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Rechnung DE02342 in Mrz
Integration Provider
| Total SHS | [21 empty] | 15000
[22 empty] | 2712.4 |  |  | 19867.2 | total value Alberto reported
[21 empty] | SOW | Charging 03/2025 |  |  |  | total costs
total costs - Feb value
FY25 Support US Sonderbudget
| Helbing, Björn | Cost rate 130,00 (PCT) | [13 empty] | 10400 | 8840 | 10400 | 10400 | 10400 | 8060
|  | Sell rate 148,00 charging | [13 empty] | 11840 | 10064 | 11840 | 11840 | 11840 | 9176
14%
| Swoboda, Claudia | Cost rate 100,00 (PCT) | [13 empty] | 10000 | 8000 | 10000 | 10000 | 10000 | 8400
|  | Sell rate 114,00 charging | [13 empty] | 11400 | 9120 | 11400 | 11400 | 11400 | 9576
14%
|  | Total cost rate | [20 empty] | 118450
| Total US | Charging | [20 empty] | 124373
Andrea fragen, wie sie verrechnet (cost rate +5%?)
FY25 Support China Sonderbudget
| Helbing, Björn | Cost rate, 130,00 (PCT) | [13 empty] | 2600 | 2600 | 2600 | 2600 | 2600 | 2600
|  | Sell rate 148,00 charging | [13 empty] | 2960 | 2960 | 2960 | 2960 | 2960 | 2960
|  | Total cost rate | [20 empty] | 15938
| Total CN | Charging | [20 empty] | 16735
TOTAL Cost
TOTAL Sell
Operations - total costs for PowerBI reporting
| DPS Reporting - ACT Cost month | [14 empty] | 23000
| DPS Reporting - ACT Cost YTD | [14 empty] | 23000
Note on G10: Swoboda, Claudia (GBS H2R DPS 2 1): Invoice DE02342 vom 09.04.2025
Note on Q17: Swoboda, Claudia (GBS H2R DPS 2 1): 80 Std.
Note on R17: Swoboda, Claudia (GBS H2R DPS 2 1): 68 Std.
Note on V17: Swoboda, Claudia (GBS H2R DPS 2 1): 62 Std * 130 =8.060
Note on Q20: Swoboda, Claudia (GBS H2R DPS 2 1): 100 Std
Note on R20: Swoboda, Claudia (GBS H2R DPS 2 1): 80 Std.
Note on Q29: Swoboda, Claudia (GBS H2R DPS 2 1): 20 Std
Note on R29: Swoboda, Claudia (GBS H2R DPS 2 1): 20 Std.

## Umlage
| Current |  | 8.5% |  | Update 02/2025
Services (Operation) für Umlage: | Services (Operation) für Umlage: | Revenue FC24 | Total DPS allocations | Monatlich | Services (Operation) für Umlage: | Revenue FC24 | Total DPS allocations | Monatlich
TMS, OP | TMS, OP | 1431552 | 111452.9087 |  | TMS, OP | 1431552 | 111452.9087
TMS Project, Projekt | TMS Project, Projekt | 2309175 | 179779.8965 |  | TMS Project, Projekt | 2309175 | 179779.8965
Aufteilung auf Projekte | Aufteilung auf Projekte |  |  |  | Aufteilung auf Projekte
Eightfold Crew (75%) | Eightfold Crew (75%) |  |  |  | Eightfold Crew (75%)
Avature Crew (25%) | Avature Crew (25%) |  |  |  | Avature Crew (25%)
Employee Services

## OP - 1st Lvl Supp
# | Role | Location | TMS Operations | Yearly working hours | Weekly working hours | Cost Rate | Yearly FLC CZ | Comment | DPS Profit Margin (5%) | Total Service Price
1 | IT Support Specialist (AOS) | CZ - PRG S | 100% | 1680 | 40 | 43 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
2 | IT Support Specialist (AOS) | CZ - PRG S | 100% | 1680 | 40 | 43 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
3 | IT Support Specialist (AOS) | CZ - PRG S | 100% | 1680 | 40 | 43 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
4 | IT Support Specialist (1st level) | CZ - PRG S | 100% | 1680 | 40 | 41 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
5 | IT Support Specialist (1st level) | CZ - PRG S | 100% | 1680 | 40 | 41 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
6 | IT Support Specialist (1st level) | CZ - PRG S | 100% | 1680 | 40 | 41 |  | Yearly FLC CZ include all employee costs +7,5% CZ profit margin +7,5% PCI increase
Total Costs
| DPS Profit Margin | 5%
DE
CZ
total profit margin
| Cost Charging to Customer | Total Service Price | % | Yearly
| GBS H2R US |  | 34.3
| GBS H2R CN |  | 4.6
| P&O ECO DIG |  | 61
total
# | Open issues | Responsible | Status | Due Date | Comment
1 | Which tool will be used for external case management? | Amanda | in progress |  | 18.04.2024: Amanda: oHRSP will stay for external tickets
2 | Does DPS adds DPS profit margin (5%) on top? | Björn | in progress | 2024-04-26
3 | Ticketing tool for CN and AA region | Amanda | in progress |  | Siemens GBS China supports ASEAN region Because Siemens GBS China does not move to People Center they cannot support ASEAN region after migration
4 | Simona proposed 6. person from CZ to support ASEAN region except China | Björn | done | 2024-04-25 | Confirmed to Amir, Erika, that 6. person not needed today; can change in furute due to ReimagineTA, IC-Portal go-live or SHS transition
5 | Will DE Umlage (7.5%) be added to FLC of CZ colleagues? | Adam | done | 2024-04-24 | DE Umlage not added to FLC for CZ; see his email
6 | With whom do we align the hourly rates of support colleagues? | Adam | done |  | DPS calculates them; inform Erika/Amir
7 | Do we add DPS profit margin (5%) to CZ costs | Adam | done |  | yes
8 | Confirmation from GBS H2R US for cost charging in FY25 | Scott | open
9 | Confirmation from GBS H2R CN for cost charging in FY25 | Lexi | open |  | 18.4. For commercial part, no service cost increase for customers, keep flat to €24,710 for 2 tier support internal charging (DPS& CZ team).
10 | Access to ServiceNow for GBS H2R CN to deliver 1st level agent service to AA countries which have implemented ServiceNow | Lexi | open |  | 29.4. Lexi will contact Harry to clarify in week May 6th and 10th
11 | China local ticket tool to support for China mainland, HK, TW | Lexi | open |  | 29.4. mid of May Lexi comes back with more details (vendor selected; already used for Siemens China IT)
12 | How does technical solution oHRSP/PEP is defined? | Mirka, Meryem | open

## Supp CZ - TMS Exp
| 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | Actual FY25
Support CZ
Minarcik, Jiri
Nová, Miroslava
Augusto da Silva, Amanda
Timkova, Jarmila
Strojny, Tomasz Lech
Fernandes Redondo, Amanda
Matos, Paula
Costa, Bruno
Conceicao, Ana (ext)
TMS Experts
Minarcik, Jiri
Nová, Miroslava
Augusto da Silva, Amanda
Timkova, Jarmila
Strojny, Tomasz Lech
Fernandes Redondo, Amanda
Matos, Paula | 2025-05-01: 46
Costa, Bruno | 2025-05-01: 840
Conceicao, Ana (ext)
Support/TMS Experts CZ - charging to GBS CN H2R (China)
Support/TMS Experts CZ - charging to GBS H2R US (USA/Canada)
Support/TMS Experts CZ - charging to P&O ECO DIG

## Productivity
[5 empty] | FY24 |  |  | FY25
Ramp down Eightfold | [7 empty] | SOW#4
Productivity | Eightfold Crew | Savings | Costs in FY25 |  | March 2024 | SOW#2 SE for EE Ops
stop booking Feb - Sep 2025 | Pires Rosa, Claudia (ext) | 51000
| Matos Oliveira, Ana Rita | 38250
| Testing |  | -5100
| Helbing, Björn (33%) | 47840
| Zouine, Meryem | 67678
| Bicho, Rita (33%) | 22559
| Service Management |  | -13944
for remaining activities
| JCC | 5000
| DirX | 20000
| Total |  |  |  | SOW#3 | June 2024
[10 empty] | FY24 | 187706
[10 empty] | FY25 | 140442
new tasks:
- Preboarding Project
- support in other remaining Avature change requests
Costs
[9 empty] | Eightfold | 1. Q | 140442 | 140442
[10 empty] | 2. - 4. Q | 421326 | 160000 | Productivity
[12 empty] | 300000 | agrreed with P&O
|  | FY24 | FY25 | Savings
| Eightfold | 276118 | 114914
| TuPu | 15773 | 0 | [5 empty] | Avature |  | 240000
| Avature | 1033627 | 1311461
43150
144556
25% of every CR / Project | Eightfold Crew |  | 25%
Oct 24 - March 25 | FTE | 89580
| Int. Provider | 2427
| ext. Provider (Eightfold) | 0 | 0
Avature Crew
| FTE | 120734
| Int. Provider | 3871
| ext. Provider (Avature) | 0 | 0
Avature ext. Careers Portal Crew
| FTE | 22228
| Int. Provider | 0
| ext. Provider (Avature) | 0
Avature Preboarding
| FTE | 5986
| Int. Provider | 0
| ext. Provider (Avature) | 0

## VCC
VCC | FY25 | FY26
lower costs to the customer |  | Eightfold
25% of every CR

## TuPu Calc
Phase |  | Scope Position | Unit (e.g. NO. of Recruiters) | Unit Cost | Units S'Industry | Total S'Industry € | Sum (gross)€ VAT:6%
Year 5 | Recurring | WeChat platform(ENG&CHN) | Fixed | 3587.15 | 1
|  | China Job Portal |  | 3587.15 | 1
|  | SMS Service(30,000messages) |  | 179.36 | 1
|  | Intergration Maintenance |  | 1425.09 | 1
|  | MyID Intergration |  | 427.77 | 1
|  | Job Distribution & Sourcing | # of Recruiters | 608.38 | 39
|  |  |  | 506.99 | 16
Including 15 accounts for SHS
Business | Initially defined | Prolongation |  |  | Total
2023-12-16
SAG | 40 |  | SAG | 40 | 40 | without innomotics
SHS | 15 |  | SHS | 15 | 15
Total | 55 |  |  | 55 | 55
EUR | 43508 |  |  |  | 43508

## TuPu Lic - History
# | Phase |  | Scope Position | Unit (e.g. NO. of Recruiters) | List Unit Price (€) | Unit Cost After Discount | Discount Rate | Accounts Range | Units | Total (net) € | Sum (gross) € VAT:6% | Service Range
1 | Year 2 | Recurring | Job Distribution & Sourcing | # of Recruiters | 1013.97 |  | 40% | 1-39 Users | 0 |  |  | 12 months
[7 empty] | 50% | 40-69 Users | 0
[7 empty] | 60% | 70-99 Users | 19
[6 empty] | 380 | fixed fee | 100-200 Users | 1
Total
| Business | Initially defined | Additional added |  |  | Additional added |  |  | Additional added |  |  | Total
FY21 |  |  | 2020-12-01 |  |  | 2021-06-11 |  |  | 2021-09-09
First year | SAG | 25 | 40 | SAG | 24 | 14 | SAG | 10 | 10 | SAG | 10 | 69
| SHS | 0 |  | SHS | 16 |  | SHS | 4 |  | SHS | 0 | 20
| SE | 5 | 0 | SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 5
| Total | 30 | 40 |  |  | 14 |  |  | 10
| Ground Total | [10 empty] | 94
| Business | Initially defined | Prolongation |  |  | Additional Required |  |  | Prolongation |  |  | Prolongation |  |  | Total
FY22 |  |  | 2021-12-01 |  |  | 2022-05-11 |  |  | 2022-06-11 |  |  | 2022-09-09
Second year | SAG | 25 | 40 | SAG | 24 | 6 | SAG | 6 | 14 | SAG | 10 | 10 | SAG | 10 | 75
| SHS | 0 |  | SHS | 16 |  | SHS | 0 |  | SHS | 4 |  | SHS | 0 | 20
| SE | 5 | 0 | SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 5
| Total | 30 | 40 |  |  | 6 |  |  | 14 |  |  | 10
| Ground Total | 30 | 39 + 1 |  | 70 | [9 empty] | 100
| EUR | 19347 | 22357 |  | 41704 |  |  | 19 + 1 |  |  | 8572 |  | 10 | 4300
| Business | Initially defined | Prolongation |  |  | Prolongation |  |  | Prolongation |  |  | Prolongation |  |  | Total
FY23 |  |  | 2022-12-01 |  |  | 2023-05-11 |  |  | 2023-06-11 |  |  | 2023-09-09
Third year | SAG | 25 | 40 | SAG | 24 | 6 | SAG | 6 | 14 | SAG | 10 | 10 | SAG | 10 | 75
| SHS | 0 |  | SHS | 16 |  | SHS | 0 |  | SHS | 4 |  | SHS | 0 | 20
| SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 0 | SE | 0 | 0
| Total | 25 | 40 |  |  | 6 |  |  | 14 |  |  | 10
| Ground Total |  |  |  | 65 |  |  | 71 |  |  | 85 |  |  | 95 | 95
| EUR |  |  | 39 + 26 | 39124 |  | 4 + 2 | 3010 |  | 14 | 6019 |  | 10 | 4300
FY24
4th year
| Business | Initially defined | Prolongation |  |  | Total
2023-12-16
| SAG | 60 |  | SAG | 60 | 60
| SHS | 15 |  | SHS | 15 | 15
| Total | 75 |  |  | 75 | 75
| EUR | 43508 |  |  |  | 43508
FY25 | Business | Initially defined | Prolongation |  |  | Total
5th year |  |  | 2023-12-16
| SAG | 40 |  | SAG | 40 | 40 | without innomotics
| SHS | 15 |  | SHS | 15 | 15
| Total | 55 |  |  | 55 | 55
| EUR | 43508 |  |  |  | 43508

## TA_TM SM FY23_Stand 02_23 (hidden)
FY23 - Status 09.02.2023 | Company | Responsibilty / Tasks | Hourly costs | Hours per year | % in Service | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | FC TA/ TM Service FY23 | Reporting to Steffi Biegel, 09.03.2022 | Reporting to Steffi Biegel, 07.07.2022 | GBS H2R DPS Profit in EURO | GBS H2R DPS Profit in % | Reporting to Steffi Biegel, 07.11.2022 | Reporting to Steffi Biegel, 06.03.2023 | Comment | Cost Forecast
1st Level Support | GBS | [17 empty] | 216000 | 216000 |  |  | 216000
Addl. 1st Level Support (2 FTE) due to EF Go-Live 1 | GBS | [23 empty] | Erhöhung mit Renate und Steffi abstimmen
Application Support | GBS | [17 empty] | 130534 | 130534 |  |  | 130534
CA/US support SE | [18 empty] | 46750 | 46750 |  |  | 46750 |  | Mit Renate, Steffi klären, dass Position of 0 reduziert wird
Support GBS H2R | [18 empty] | 393284 | 393284
Bruno Costa Ferreira (ext) | GBS O DS BPM IMS |  | 40 | 1600 | 100% | 2022-10-01: 6320; 2022-11-01: 5700; 2022-12-01: 6360; 2023-01-01: 6670 |  | 75200 | 75200 |  |  | 64000 | 64000
Paula Matos | GBS O DS BPM IMS |  | 40 | 1600 | 100% | 2022-10-01: 3764; 2022-11-01: 4244; 2022-12-01: 3390; 2023-01-01: 2148 |  | 75200 | 75200 |  |  | 64000 | 64000 | Abstimmung mit Amanda, Claudia und Björn, da Paula nicht 100% auf TA Landscape kontiert
Douglas Pedreira (ext) - until 17.02.2023 | GBS O DS BPM IMS |  | 42 | 1600 | 100% | 2022-10-01: 7014; 2022-11-01: 0; 2022-12-01: 5712; 2023-01-01: 6720 |  | 75200 | 75200 |  |  | 67200 | 67200
addtl. Support (0,5 FTE) | GBS O DS BPM IMS |  | 42 | 1600 | 100% | [13 empty] | 75200 | 75200 |  |  | 33600 | 33600
Others | GBS H2R DPS C05 |  |  |  |  | 2023-01-01: 730.75 |  | 0 | 0
2nd Level Support | [18 empty] | 225600 | 225600
5%
Rita Bicho | GBS O DS BPM STC | Requirements Engineering and Test Management | 40 | 1600 | 0% | [13 empty] | 0 | 0 |  |  |  | 0
Filipe Guerreiro Luis Pires | GBS O DS BPM STC | Requirements Engineering and Test Management | 32 | 1600 | 100% | 2022-10-01: 3360; 2022-11-01: 4928; 2022-12-01: 4256; 2023-01-01: 4928 |  | 62400 | 62400 |  |  | 51200 | 51200
Daniel Magro | GBS O DS BPM STC | Requirements Engineering and Test Management | 40 | 1600 | 50% | 2022-10-01: 3200; 2022-11-01: 3040; 2022-12-01: 2720; 2023-01-01: 2720 |  | 31200 | 31200 |  |  | 32000 | 32000
Rodrigo Coutinho | GBS O DS BPM STC | Requirements Engineering and Test Management | 40 | 1600 | 50% | 2022-10-01: 3360; 2022-11-01: 3520; 2022-12-01: 3520; 2023-01-01: 3520 |  | 31200 | 31200 |  |  | 32000 | 32000
addtl. tester (0,5 FTE) | GBS O DS BPM STC | Requirements Engineering and Test Management | 40 | 1600 | 100% | [13 empty] | 31200 | 31200 |  |  |  | 32000
Testing | [18 empty] | 124800 | 124800
5%
Amanda Fernandez | GBS H2R DPS C01 | TA/TM Service Management | 72 | 1600 | 95% | 2022-10-01: 3920; 2022-11-01: 8295; 2022-12-01: 4130; 2023-01-01: 8715 |  | 144000 | 144000 |  |  | 152000 | 152000
Claudia Swoboda | GBS H2R DPS C01 | TA/TM Service Management | 95 | 1600 | 50% | 2022-10-01: 5130; 2022-11-01: 6460; 2022-12-01: 5415; 2023-01-01: 6175 |  | 79200 | 79200 |  |  | 76000 | 76000
Christine Kaiser | GBS H2R DPS C01 | TA/TM Service Management | 95 | 1600 | 0% | [13 empty] | 64800 | 0 |  |  | 0 | 0
Jan Loerinc (Accenture) | GBS H2R DPS C01 | TM Service Management Support | 68 | 1650 | 50% | 2022-10-01: 9560; 2022-11-01: 9560; 2022-12-01: 9560; 2023-01-01: 9560; 2023-02-01: 9560; 2023-03-01: 9560 |  | 0 | 51000 |  |  | 60000 | 60000 | Fixprice
Jan Loerinc (Accenture) - prolongation | GBS H2R DPS C01 | TM Service Management Support | 68 | 1650 | 50% | 2023-04-01: 9560; 2023-05-01: 9560; 2023-06-01: 9560; 2023-07-01: 9560; 2023-08-01: 9560; 2023-09-01: 9560 |  | 0 | 51000 |  |  | 60000 | 60000 | Fixprice
CERT check (Pentest) (for AI-TM Project FY23 additional Pentest planned) | [5 empty] | 2023-09-01: 40000 | [5 empty] | 30000 | 30000
IT others (HR Umlage) | [5 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | [5 empty] | 120000 | 120000 | covered in IT SM budget | internal booking
Service Management | [18 empty] | 288000 | 390000 |  |  |  |  | covered in IT SM budget
5%
DirX | [5 empty] | 2022-10-01: 820; 2022-11-01: 401.5
CHCM
JCC | [5 empty] | 2022-10-01: 26.25
Others
Change Management | [18 empty] | 288000 | 390000 |  |  |  |  | covered in IT SM budget
Avature Total (bis 31.03.2023) 9707302823 | [18 empty] | 1974000 | 1800000 |  |  | 1860000 | 1860000
Annual Subscription Fee Global (w/o US/CA) CRM, ATS (bis 31.03.2023) | Avature | ATS & CRM |  |  |  | 2022-10-01: 375000; 2023-01-01: 375000 |  | 1500000
Annual Subscription Fee US/CA €228.559 (bis 31.003.2023) | Avature | US and CA ATS/CRM |  |  |  | 2022-10-01: 63500; 2023-01-01: 63500; 2023-04-01: 0; 2023-07-01: 0 |  | 254000 | [5 empty] | Klärung mit Sara, ob Position in ATS/CRM Fee integriert ist
Video Interviewing - 9706301876/9706762788 (Ersatz) (bis 31.03.2023) | Avature | Video Interviewing |  |  |  | 2022-10-01: 17500; 2023-01-01: 17500 |  | 100000
Preboarding / Onboarding | [5 empty] | 2022-10-01: 30000; 2023-01-01: 30000
Avature Total (ab 01.04.2023) PO offen !! | bar: 2023-04-01; 2023-07-01
Annual Subscription Fee Global (incl. US/CA) CRM, ATS | Avature | ATS & CRM
Decommisioning of demo instance | [5 empty] | 2023-04-01: -2500; 2023-07-01: -2500
Preboarding / Onboarding € 107.080 | Avature | Preboarding | [16 empty] | 120000
Video Interviewing € 70.000 | Avature | Video Interviewing |  |  |  | 2023-04-01: 17500; 2023-07-01: 17500
add. Custom Integrations: Tupu, Visage, Pulse | [18 empty] | 0
add. Custom Integrations: Exh. 14 (Teamio, Eightfold) | [18 empty] | 0 | [5 empty] | allocation with go-live
add. Custom Integrations: Exh. 16 (HR D2GO, EF LL) | [24 empty] | allocation with go-live
Removal 2x internal career site -€15.000 (ab FY24)
Eightfold - 9706598533 (bis 30.09.2024) - 810.000 | Eightfold | Ext. Portal, div. Portale |  |  |  | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 |  | 810000 | 810000 |  |  | 810000 | 810000
iCims (Jibe, incl. Ruutly) - 9707295940 - $400.820 (€375.000 /1,07) | iCims/Jibe | External candidate portal |  |  |  | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 | 33402 |  | 0 | 180000 |  |  | 400820 | 400820
Tupu (TRE) | Tupu |  |  |  |  | 2022-12-01: 48883 |  | 72000 | 74000 |  |  | 74000 | 74000
SAG Subscription fee 3rd year | [5 empty] | 2022-12-01: 9759
SAG Licenses (39+26) | [5 empty] | 2022-12-01: 39124
S'Energy | [5 empty] | 2022-12-01: 0
eQuest - 103.000 € / 9707285832 | [18 empty] | 103008 | 103008 |  |  | 140000 | 140000
Premium Data Report for SAG (pro rata to 30.03.2022) 3.500 € | [5 empty] | 2023-02-01: 3500; 2023-09-01: 0 |  | 6000 | 6000
Automated XML feeds 28.542 € | [5 empty] | 2023-03-01: 28542 |  |  | 30000
Renewal Oct 2023: 143.250 €
Adobe Sign | [5 empty] | 2023-09-01: 70000 |  | 33000 | 70000 |  |  | 70000 | 70000
Integrations Provider | [18 empty] | 2428819.5
5%
MyLearningWorld | Infosys | LXP integration |  |  |  | 2023-09-01: 20000 |  | 20000 | 20000 |  |  | 100000 | 100000 | covered in Avature Addons (100T€) | tbd.
Siemens SMTP (Mailgateway Tupu, EF (ab 01.04.2023), Avature (tbd.) | [18 empty] | 8000 | [5 empty] | covered in Avature Addons (100T€) | internal booking
Wiki (TA Wiki; ALM Archive) | [18 empty] | 2100 | [5 empty] | covered in Avature Addons (100T€) | internal booking
Siemens IT - DirX direct charge Avature and EF, GBS H2R DPS others (Certificates, SCD) | [5 empty] | 2555 | 2555 | 2555 | 2555 | 4010 | 4010 | 4010 | 4010 | 4010 | 4010 | 4010 | 4010 |  | 168711.5 | 80000 |  |  |  |  | covered in Avature Addons (100T€) | internal booking
JCC (Proxy for ICSR) | GBS H2R DPS C07 | Siemens landscape Integrations | [16 empty] | 18000 | 9000 |  |  |  |  | covered in Avature Addons (100T€) | internal booking
SOC | GBS | SOC integration |  |  |  | 2023-09-01: 0 |  | 0 | 0
Integrations SAG | [18 empty] | 2428819.5
Integrations total | [18 empty] | 2428819.5
5%
Accessibility test | T | [17 empty] | 0 | 0
Translations | GBS BPS | [17 empty] | 0 | 0
Travel & Hospitality | [18 empty] | 0 | 0
Incentive & Recognition | [18 empty] | 0 | 0
Additional costs | [18 empty] | 60000
Total Budget | [18 empty] | 3520503.5
total DPS Budget | [18 empty] | 3127219.5
5%
Legend
Forecast
Actuals
covered in GBS budget
covered in P&O budget
Todos
Serie mit Steffi einladen
Serie mit Anke Bartelheimer einladen
Katrin Schubert einladen in Meetings mit Steffi Biegel
PSP-Elemente in "Steffi-Datei" aktualisieren
Profit für Projekt fehlt
Travel Costs - Handling (PT, Vendoren, Barbara, Renate) mit P&O abstimmen
Note on X12: Swoboda, Claudia (SOP IT APD HRS C05): 3 FTE 64.000 64.000 67.200 =195.200 zuzgl. 5% =204.960 0,5 FTE zusätzlich für AI-TM 32.000 zuzügl. 5% = 33.600 Summe: 238.560
Note on X19: Swoboda, Claudia (SOP IT APD HRS C05): 2 FTE 51.200 32.000 32.000 =115.200 zuzügl. 5% = 120.750 0,5 FTE zusätzlich für AI-TM 32.000 zuzügl. 5% = 33.600 Summe= 154.350
Note on X28: Swoboda, Claudia (SOP IT APD HRS C05): 1,5 FTE 152.000 (Amanda) 76.000 (Claudia 50%) +Umlage 120.000 +Pentest 30.000 = 378.000 1 FTE zusätzlich für AI-TM 120.000 zuzügl. 5% = 126.000 (Jan) Summe = 504.000 oder 2 FTE 152.000 (Amanda) 126.000 (Jan) +Umlage 120.000 +Pentest 30.000 = 428.000 0,5 FTE zusätzlich für AI-TM 76.000 (Claudia 50%) Summe = 504.000
Note on X34: Swoboda, Claudia (SOP IT APD HRS C05): 1,5 FTE 152.000 (Amanda) 76.000 (Claudia 50%) +Umlage 120.000 +Pentest 30.000 = 378.000 1 FTE zusätzlich für AI-TM 120.000 zuzügl. 5% = 126.000 (Jan) Summe = 504.000 oder 2 FTE 152.000 (Amanda) 126.000 (Jan) +Umlage 120.000 +Pentest 30.000 = 428.000 0,5 FTE zusätzlich für AI-TM 76.000 (Claudia 50%) Summe = 504.000
Note on K66: +1455,- € für EF ab Go-Live